## Final Content Calender (Septemb
September 2026 Content Calendar
Date | Day | Product / Focus | AIPE Pillar | Format | Content Type | RTM / Campaign Objective | Content Gist & Creative Direction | Content Link | Budget | Platform | Boosting Budget
01-Sep-2026 | Tue | FZS V2 (DD), FZS V4, FZS Hybrid, FZ25, FZ-X, Fazer | Offer Post | Static + Motion | Static | Month Kick-off | Month-opening offer announcement. One clean static/motion carousel revealing September price and EMI schemes across all six priority models in one place, so a browsing customer can shop the whole range from a single post. CTA: 'Visit your nearest showroom this September.' Sets the tone that this is a purchase-forward month. | https://drive.google.com/drive/folders/1ycC_iuAnzjbOLCaDNJoj9cNkSuf57GaL
03-Sep-2026 | Thu | FZS Hybrid | Interest | Reel | Short-form Video | Cyan Mettalic | FZS FI Hybrid Lifestyle Trend | https://drive.google.com/file/d/1MzaPzDKlmiaYQqAZAkZOvQaYTrZJsf8T/view?usp=drive_link
09-Sep-2026 | Wed | FZS V4 | Interest | Reel | Short-form Video | Magesty Red | Interest Generation Content Straightforward conversion content for the second half of the bread-and-butter pair. | https://drive.google.com/file/d/1wV5mjttaBbFEUj6iZiw5MKGpmVIOYNc-/view?usp=drive_link
2026-09-04 | Fri | FZS V2 | Experience | Reel | Long-form Video | Dark Knight | Customer Success Story Documentary Featuring a Yamaha Bike. Showcase how Yamaha bike has supported a customer’s journey, success, and achievements.
05-Sep-2026 | Sat | FZ25 | Experience | Motion Video | Short-form Video | Racing Blue | FZ 25 Lifestyle OVC. Showcasing real customer story in a cinematic storytelling way
06-Sep-2026 | Sun | FZS V2 (DD) | Purchase | Reel | Short-form Video | Multiple Color | Model-specific offer post — price, EMI, and exchange scheme with a clear showroom-enquiry CTA. FZS V2 is the volume engine; this is a straightforward conversion post, not a story post.
2026-09-07 | Mon | FZ-X | Experience | Reel | Long-form Video | Matte Blue | FZX Rajshahi Couple Video. Portray 62% of FZ-X target demographic, who are married with emotional content.
08-Sep-2026 | Tue | Fazer | Awareness | Carousel | Static | Burning Red | Repositioning carousel. Stops describing Fazer as 'a smaller FZS' and instead leads with what it alone offers: comfort-first ergonomics and practical daily-use value. Core purpose: give a lapsed-consideration buyer a fresh reason to look again, separate from the FZS family.
11-Sep-2026 | Fri | FZS Hybrid | Interest | Motion Video | Long-form Video | Cyan Blue | Feature communication of the TFT meter and multimedia functionality and its real life benefits. | Yamaha Reel 2 4k 28-08-2026.mp4
12-Sep-2026 | Sat | FZ-X | Interest | Carousel | Static | Matte Blue / Matte Titan | Retro-modern styling and long-route lifestyle carousel — positions FZ-X for a rider who wants something visually distinct from the FZS line. Core purpose: build consideration through identity, not spec sheet.
2026-09-13 | Sun | FZ25 | Interest | Reel | Long-form Video | Racing Blue | "FZ 25 Get Together " Experience Sharing of existing customers and creating both online and offline buzz about the product
14-Sep-2026 | Mon | FZS V2 (DD) | Experience | Long-form Video | Long-form Video | Black Metallic | FZ V2 Customer Lifestyle Review. To showcase an authentic customer experience with Yamaha FZS Version 2
15-Sep-2026 | Tue | FZ25 | Interest | Carousel | Static | Racing Blue | Spec-and-performance comparison carousel against the higher-cc segment it competes in (Dual Channel ABS, engine character). Core purpose: reassert why FZ25 is the aggressive/speed choice now that awareness has been rebuilt — this is where the brief's positioning direction actually lands.
2026-09-16 | Wed | MT15-V2 | Experience | Reel | Long-form Video | Metallic Black | MT 15 "The Moment That Move Us" "Build an always-on customer engagement platform that encourages R15 and MT15 riders to share their photos, reels, riding moments and personal memories. "
17-Sep-2026 | Thu | FZS V4 | Interest | Motion Video | Short-form Video | Matte Black | Feature reminder as the monsoon tapers off: TCS and ABS framed around 'control on the last wet roads of the season.' A light touch — not a full campaign — to keep V4's tech differentiation visible against V2 and Hybrid.
19-Sep-2026 | Sat | MT15-V2 | Interest | Reel | Short-form Video | Metallic Black | AI VIDEO ON THE TECHNOLOGY AND AESTHETIC OF THE DARK KNIGHT
20-Sep-2026 | Sun | Multiple Model | Interest | Motion Video | Short-form Video | World Cleanup Day | Feature content on fuel economy and touring comfort — the two things Fazer owners consistently value. Core purpose: follow the Sep 8 awareness post with a concrete reason to consider, before any offer messaging.
22-Sep-2026 | Tue | FZS Hybrid | Purchase | Reel | Short-form Video | Matte Black | September offer + EMI post backed by hybrid convenience and technology value. This is where two weeks of myth-busting and fuel-saving Interest content should start converting — placed deliberately in the seasonal purchase-peak window.
23-Sep-2026 | Wed | R15 Series | Purchase | Reel | Short-form Video | Metallic Grey | Theme Based MT15 and Product shoot content by AI, AI-generated thematic visual content cost-effectively delivers studio-quality aesthetic shoots for the R15 and MT-15, tailored to capture the visual preferences of Gen Z and young riders. This strategy drives targeted brand awareness, elevates product desire, and boosts digital engagement without the heavy production expenses of traditional shoots. Want to make that content by DM team.
24-Sep-2026 | Thu | FZS V2 (DD) | Experience | Reel | Short-form Video | Dark Knight Red | CUSTOMER REVIEW (distinct from the Sep 14 ride review) — a real owner talks about day-to-day ownership: service experience, resale confidence, how the bike has held up. Core purpose: trust and ownership confidence rather than performance — this is the proof a hesitant buyer needs.
2026-09-25 | Fri | FZX | Experience | Reel | Long-form Video | Matte Titan | FZX Lifestyle Review, Showcasing FZX as a lifestyle product
26-Sep-2026 | Sat | FZ25 | Purchase | Reel | Short-form Video | Racing Blue | September offer CTA — the close of a three-post FZ25 arc this month (Awareness on Sep 5, Interest on Sep 15, Purchase here). Core purpose: convert the visibility rebuilt earlier in the month rather than opening with price.
27-Sep-2026 | Sun | Multiple Model | Interest | Reel | Short-form Video | World Tourism Day | World Tourism Day tie-in. Connects FZ-X's long-route, retro-modern identity to responsible discovery and local journeys — emotional/lifestyle register, not a sales post. Core purpose: reinforce FZ-X's touring identity on a day the audience is already primed for travel content.
2026-09-28 | Mon | R15 Series | Experience | Reel | Long-form Video | Metallic Grey | Racing Perfectionist Meet Up - Cultivate brand loyalty and performance culture among R-Series owners by creating an exclusive platform that strengthens community connection and generates organic user advocacy.
29-Sep-2026 | Tue | FZS V4 | Experience | Reel | Short-form Video | Matte Black | CUSTOMER REVIEW — an owner's honest take on long-term ownership (control, comfort on daily commutes, confidence in the ABS system). Core purpose: proof-of-ownership content to sit alongside the month's purchase pushes.
30-Sep-2026 | Wed | FZS Hybrid | Experience | Long-form Video | Long-form Video | Cyan Metallic | Early-owner testimonial — Hybrid launched only in February, so this is one of the first real customer voices the brand can put forward. Even a small pool of owners builds crucial social proof going into Q4. Closes the month having taken Hybrid through a full Interest→Purchase→Experience arc.
|  | Pillar | Post Count
|  | Awareness | 1
|  | Interest | 10
|  | Purchase | 4
|  | Experience | 10
|  | Total posts | 26

## Product Team
Date | Day | Content | A.I.P.E Pillar | Content Objective | Shoot Date | Publish Date | Color Concern | Format | Budget | Platform | Product | Drive Link | Remarks | Boosting Budget | Column 1
August |  | Life Style Review | Interest | To showcase an authentic customer experience with Yamaha FZS Version 2 | 2026-07-26 | 2026-08-08 | Dark night | Product Review | 15000 | Facebook | FZS V2
August |  | Customer Review | Interest+Experience | Showcase real customer experience, authenticity, and guidelines for future riders | 2026-08-01 | 2026-08-25 | R15 V3 Racing Blue | Product Review | 15000 | Facebook | R15
August |  | Customer Review | Awareness+Interest | Expressing the real customer advocacy, establishing as a testimonial supported by original customer experience. | 8/1/26 8/4/26 8/5/26 8/7/26 8/8/26 8/14/26 | 8/20/26 8/22/26 8/24/26 8/26/26 8/28/26 | Blue+Black | Product Review | 15000 each Total 200,000 | Facebook | FZ 25
August |  | Life Style Review | Interest | Lifestyle Review | 21/8/2026 | 25/8/2026 | Blue | Product Review | 15000 | Facebook | FZX
August |  | Influencer Collaboration | Awareness | Content Series: CAMPAIGN FLOW ● EPISODE 01 — Purchase & Choice: “িনেজর ride. িনেজর choice.” ● EPISODE 02 — Attention & Design: “িকছু bike আসার সােথ সােথই নজের পেড়।” ● EPISODE 03 — Personality & Lifestyle: “Ride that feels like you.” ● EPISODE 04 — Product Knowledge: “সবাই expert না। িকছু িজিনস িনেজ experience করেত হয়।” ● EPISODE 05 — Riding Experience: “িকছু ride-এর জন্য reason লােগ না।” ● EPISODE 06 — Purchase Consideration: “Reason অেনক থাকেত পাের. শষ পযন্ত choiceটা িনেজর।” ● EPISODE 07 — Design & Visual Appeal: “দখেল ছিব তুলেত ইচ্ছা করেবই।” ● EPISODE 08 — Ownership & Pride: “FZ-X — আলাদা হওয়ার একটা কারণ আেছ।” | TBA | TBA | FZX Blue | Special Content | [6 empty] | - Content schedule for August 2026 highlighting Yamaha motorcycle models including FZS, R15, FZ 25, FZX, and MT - Focuses on driving brand awareness, customer interest, and engagement through authentic user experiences - Features diverse formats including customer reviews, lifestyle OVCs, influencer collaborations, reels, and community events - Utilizes Facebook, YRC Page, and TikTok as key promotional platforms with assigned production budgets
August
August |  | Lifestyle Review | Interest+Experience | To build premium mindset and make emotional connection | 8/5/26 and 8/23/26 | TBA | R15 M | Special Content | 65000 | Facebook | R15
August
August |  | Online Content (Reels) | Interest | Empowering the next generation through authentic 1:5 ratio content designed to boost motivation, spark interest, and cultivate a sustainable lifestyle mindset. | 2026-08-05 | 2026-08-20 | R15 V3 racing Blue | Reels | 3000 | Facebook | R15
August |  | FZ 25 Spider Man Content | Awareness+Interest | Establishing Offline Activation, UGC Content, grabbing regular people's attention, at the same time producing content for YRC page | 2026-08-08 | 2026-08-16 | Blue | Special Content | 125000 | YRC Page | FZ 25
August |  | R15 V4 Spider man Content | Awareness+Interest | Focusing both online and offline brand visibility, create interest to Young TG | 2026-08-08 | 8/17/26 8/20/26 8/24/26 | R15 V3 racing Blue | Special Content | 125000 | YRC Page | R15
September | P1 | FZX Lifestyle Review | Awareness+Interest | Showcasing FZX as a lifestyle product | 2026-05-09 | 2026-10-09 | Blue | Product Review | 20000 | Facebook | FZX
September |  | FZX Influencer Collaboration: Nodi | Awareness | Positioning FZX among young customers, who are 27% of total buyers | 2026-07-09 | 2026-09-09 | Blue | Special Content | 35000 | Influencer page | FZX
September | P1 | FZX Rajshahi Couple Video | Awareness+Interest | Portray 62% of FZ-X target demographic, who are married with emotional content. | Already done | 2026-02-09 | Blue | Special Content | 20000 | Facebook | FZX
August
August
August |  | FZ 25 Lifestyle OVC | Interest+Experience | Showcasing real customer story in a cinematic storytelling way | 2026-08-14 | 2026-09-15 | Black | OVC | 75000 | Facebook | FZ 25
August
August
August
August
August
August |  | Yamaha Lovers BD Tiktok Content Make | Awareness+Interest | Connecting with the untapped market, grabbing customers interest | 2026-08-20 | 2026-08-23 | Blue | Special Content | 40000 | Yamaha Lovers BD Tiktok | FZ 25
August |  | Customer review and Tiktok content | Awareness+Interest | Focusing on real life and authentic experience related content and making tiktok content for growth and mindset sustainability | 2026-08-21 | 2026-08-31 | MT15 V1 Metallic Black | Product Review | 20000 | Facebook | MT
August |  |  | Interest+Experience | Showcasing real customer story in a cinematic storytelling way
August |  | FZ 25 - 7 customer Story of Rangpur | Interest+Experience | Showcasing real customer story in a conversation+ interview storytelling way | 2026-08-23 | 2026-08-28 | Blue+Black+White | Special Content | 30000 | Facebook | FZ 25
August
August
August |  | FZ 25 Lifestyle OVC | Interest+Experience | Showcasing real customer story in a cinematic storytelling way | 2026-08-23 | 2026-08-30 | Black+Blue | Special Content | 75000 | Facebook | FZ 25
August |  | FZ 25 Get Together | Experience | Experience Sharing of existing customers and creating both online and offline buzz about the product | 2026-08-26 | 2026-09-05 | Blue+Black+White | Get Together | 80000 | Facebook | FZ 25
September |  | Customer Review lifestyle | Interest+Experience | Showcasing real customer story in a cinematic storytelling way | 2026-08-28 | 2026-09-05 | Black | Product Review | 35000 | Facebook | MT
September |  | Theme Based R15 and Product shoot content by AI | Awareness+Interest | AI-generated thematic visual content cost-effectively delivers studio-quality aesthetic shoots for the R15 and MT-15, tailored to capture the visual preferences of Gen Z and young riders. This strategy drives targeted brand awareness, elevates product desire, and boosts digital engagement without the heavy production expenses of traditional shoots. Want to make that content by DM team. | 2026-09-10 | 2026-09-15 | Dark knight, mettalic grey | Special Content | 0 | Facebook | R15
September | P1 | Theme Based MT15 and Product shoot content by AI | Awareness+Interest | AI-generated thematic visual content cost-effectively delivers studio-quality aesthetic shoots for the R15 and MT-15, tailored to capture the visual preferences of Gen Z and young riders. This strategy drives targeted brand awareness, elevates product desire, and boosts digital engagement without the heavy production expenses of traditional shoots. Want to make that content by DM team. | 2026-09-20 | 2026-09-25 | cyan storm,ice fluo vermillion, mettalic black | Special Content | 0 | Facebook | R15
September |  | R15 feature based reels by AI | Awareness+Interest | Educate riders on advanced R15 and MT-15 engineering—such as the Assist & Slipper Clutch and VVA technology—to build tech awareness, highlight key value propositions, and convert mechanical interest into purchase intent. Want to collaborate with DM team | 2026-09-17 | 2026-09-23 | Dark knight, mettalic grey | Reels | 0 | Facebook | R15
September |  | Racing Perfectionist Meet Up | Experience | Cultivate brand loyalty and performance culture among R-Series owners by creating an exclusive platform that strengthens community connection and generates organic user advocacy. | 2026-09-22 | 2026-09-26 | Dark knight, racing blue, mettalic grey | Get Together |  | Facebook | R15
September | P1 | MT 15 "The Moment That Move Us" | Awareness+Interest | Build an always-on customer engagement platform that encourages R15 and MT15 riders to share their photos, reels, riding moments and personal memories. | 2026-09-12 | 2026-09-12 | cyan storm,ice fluo vermillion, mettalic black | Engagement Related Content | 120000 | Facebook | MT
September |  | Couple Content for MT15 | Interest+Experience | MT-15 by highlighting its versatility and reliability through an authentic family story, driving emotional resonance, lifestyle connection, and brand trust among everyday riders. | 2026-09-08 | 2026-09-14 | Black | Special Content | 55000 | Facebook | MT
September |  | Product showcase (R15) | Awareness+Interest | Showcase product in DIU and HURDCO | 2026-09-23 | 2026-09-24
September | P1 | Special Delivery Celebration R15 | Awareness+Interest | Elevate the milestone of owning an R15 by capturing genuine key-handover moments, turning customer pride into powerful social proof that drives aspirational desire among potential buyers. |  |  |  |  | 25000 | Facebook | R15
September | P1 | FZ 25 Lifestyle OVC | Interest+Experience | Showcasing real customer story in a cinematic storytelling way | 2026-09-04 | 2026-09-16 | Black+Blue | Special Content | 75000 | Facebook | FZ 25
September | P1 | FZ 25 Get Together | Interest | Experience Sharing of existing customers and creating both online and offline buzz about the product | 2026-09-05 | 2026-09-09 | Blue+Black+White | Get Together | 150000 | Facebook | FZ 25
September |  | Yamaha Lovers BD Tiktok Content Make (FZ 25) | Awareness+Interest | Connecting with the untapped market, grabbing customers interest | 2026-09-11 | 2026-09-17 | Blue | Special Content | 40000 | Yamaha Lovers BD Tiktok | FZ 25
September |  | FZ 25 Product Review | Awareness+Interest | Showcasing real customer story in a conversation+ interview storytelling way | 2026-09-14 | 2026-09-21 | Blue | Product Review | 20000 | Yamaha Lovers BD Tiktok | FZ 25
September |  | FZ V2 Customer Lifestyle Review | Experience | To showcase an authentic customer experience with Yamaha FZS Version 2 | 2026-08-27 | 2026-09-07 | Black metallic | Product Review | 6000 | Facebook | FZS V2
September |  | FZ V2 Customer Review | Experience | To showcase an authentic customer experience with Yamaha FZS Version 2 | 2026-08-23 | 2026-08-03 | Dark Knight Red Sticker | Product Review | 6000 | Dealer Facebook page | FZS V2
September |  | FZ V2 Informative content | Interest | Educate customers about the key features, benefits, and performance of the FZ V2. |  | 2026-09-10 |  | Informative Content |  | Dealer Facebook page | FZS V2
September |  | Competitor Comparision Video through local influencer | Experience | Highlight FZ V2’s strengths and advantages over competitor |  | 2026-09-15 |  | Comparision Video | 3000 | Influencer page | FZS V2
September |  | Videos about competitor weakness | Experience | Highlight competitor weaknesses |  | 2026-09-17 |  | Reels | 2000 | Influencer page | FZS V2
September | P1 | Revving The Legacy | Experience | Celebrate loyal customers by recognizing and rewarding |  | 2026-09-23 |  | Special Content | 30000 | Facebook | FZS V2
September | P1 | Customer Success Story Documentary Featuring a Yamaha Bike | Experience | Showcase how Yamaha bike has supported a customer’s journey, success, and achievements. | 2026-08-28 | 2026-09-01 | Dark Knight | OVC | 35000 | Facebook | FZS V2
September | P1 | FZ V2 Customer Lifestyle Review | Experience | To showcase an authentic customer experience with Yamaha FZS Version 2 | 2026-09-30 | 2026-09-11 | Black metallic | Product Review | 15000 | Facebook | FZS V2
September |  | Revved Up Fest | Experience | Experience Sharing of existing customers and creating both online and offline buzz about the product |  | 2026-09-17 | All Colour | Get Together | 35000 | Facebook | FZS V2
September |  | Exchange Offer Content | Purchase | Create awareness about the exchange offer and encourage customers to upgrade to a Yamaha bike. | 2026-09-20 | 2026-09-23 | All Colour | Reels |  | Facebook | FZS V2
September | P1 | Hybrid Technology Explained Series | Awareness+Interest | Utilizing our experts to explain the hybrid technology to build customer credibility. | 2026-09-01 | 2026-09-03 | Cyan Metallic | Informative Content | 10000 | Facebook, Dealer Facebook page, Youtube | FZS FI Hybrid
September | P1 | FZS FI Hybrid Customer Get Together | Experience | Experience Sharing of existing customers and creating both online and offline buzz about the product | 2026-09-18 | 2026-09-22 | All Colour | Get Together | 150000 | Facebook, Dealer Facebook page, Yamaha Lovers BD Tiktok | FZS FI Hybrid
September |  | FZS FI Hybrid Test Ride | Awareness+Interest | To gain mind share in cutomers mind by allowing them to experience the bike. | 2026-09-11 | 2026-09-15 | All Colour | Test Ride | 20000 | Facebook, Yamaha Lovers BD Tiktok, Dealer Facebook page | FZS FI Hybrid
September | P1 | FZS FI Hybrid Product Review | Awareness+Interest | Showcasing real customer story in a conversation+ interview storytelling way | 2026-09-04 | 2026-09-05 |  | Product Review | 10000 | Facebook, Dealer Facebook page | FZS FI Hybrid
September |  | FZS FI Hybrid Product Review | Awareness+Interest | Showcasing real customer story in a conversation+ interview storytelling way | 2026-09-11 | 2026-09-12 |  | Product Review | 10000 | Facebook, Dealer Facebook page | FZS FI Hybrid
September |  | FZS FI Hybrid Product Review | Awareness+Interest | Showcasing real customer story in a conversation+ interview storytelling way | 2026-09-18 | 2026-09-19 |  | Product Review | 10000 | Facebook, Dealer Facebook page | FZS FI Hybrid
September |  | FZS FI Hybrid Product Review | Awareness+Interest | Showcasing real customer story in a conversation+ interview storytelling way | 2026-09-25 | 2026-09-26 |  | Product Review | 10000 | Facebook, Dealer Facebook page | FZS FI Hybrid
September | P1 | FZS FI Hybrid Customer Lifestyle OVC | Experience | Showcasing real customer story in a cinematic storytelling way | 2026-09-04 | 2026-09-13 |  | Special Content | 60000 | Facebook, Youtube | FZS FI Hybrid
September |  | FZS V4 Static & Dynamic Content Connecting the Rainy Season with ABS | Awareness+Interest | Highlight the importance of ABS and FZS V4’s safety during the rainy season. |  | 2026-08-06 | All Colour | Special Content |  | Facebook | FZS V4
September |  | Revving the Legacy – Customers Who Have Ridden 1 Lakh+ KM | Experience | Celebrate and honor Yamaha customers who have ridden 1 lakh+ km with their bikes. | 2026-08-14 | 2026-08-19 |  | Special Content | 30000 | Facebook | FZS V4
September |  | Customer Review lifestyle | Experience | To showcase an authentic customer experience with Yamaha FZS Version 4 | 2026-08-08 | 2026-08-15 |  | Product Review | 10000 | Facebook | FZS V4
September |  | Revving the Legacy – Customers Who Have Ridden 1 Lakh+ KM | Experience | Celebrate and honor Yamaha customers who have ridden 1 lakh+ km with their bikes. | 2026-08-22 | 2026-08-26 |  | Special Content | 30000 | Facebook | FZS Fezer V2

## Digital team
Date | Day | Post No. | A.I.P.E Pillar | Product Focus | Content Objective | Format | Asset/Drive Link | Remarks | Boosting budget
2026-09-01 | Tue | 1 | Offer Post | Multi-model: FZS V2 DD, FZS V4, FZS Hybrid, FZ25, FZ-X | September offer announcement with confirmed prices and a clear authorized showroom enquiry CTA. | Static
2026-09-03 | Thu | 1 | Purchase Generation | Multi-model: FZS V2 DD, FZS V4, FZS Hybrid, FZ25, FZ-X | Offer video presenting the priority range, key value cues and a direct showroom lead-generation message. | Reel
2026-09-05 | Sat | 1 | Interest Generation | FZS V2 DD | Everyday usability content highlighting comfortable ergonomics, dependable braking and practical city-riding confidence. | Motion
2026-09-07 | Mon | 1 | Lifestyle Aspiration | FZS Hybrid | World Clean Air Day communication connecting smart urban mobility with cleaner, more conscious everyday journeys—without making emission claims. | Motion
2026-09-09 | Wed | 1 | Interest Generation | FZS V4 | Feature education focused on TCS, single-channel ABS and confident control through changing city conditions. | Carousel
2026-09-10 | Thu | 1 | Customer Experience | FZS V4 | Owner review showing how the FZS V4 supports daily commuting through control, comfort and connected features. | Reel
2026-09-11 | Fri | 1 | Customer Experience | FZS V2 DD | Authentic customer review centred on easy handling, everyday comfort and long-term ownership confidence. | Reel
2026-09-13 | Sun | 1 | Purchase Generation | FZS Hybrid | Model-specific offer communication supported by Hybrid convenience, smart technology and an enquiry-focused CTA. | Reel
2026-09-15 | Tue | 1 | Interest Generation | FZ25 | Performance-led feature content focused on 249cc character, Dual Channel ABS and comfortable upright ergonomics. | Motion
2026-09-17 | Thu | 1 | Lifestyle Aspiration | FZS V4 | Premium urban lifestyle story positioning the FZS V4 as a confident everyday companion from workdays to evening rides. | Reel
2026-09-18 | Fri | 1 | Customer Experience | FZS Hybrid | Real owner experience explaining smooth start-up, convenient city use and the benefit of no external charging. | Reel
2026-09-19 | Sat | 1 | Interest Generation | FZ-X | Build consideration through retro-modern styling, comfortable ergonomics and a relaxed city-to-weekend riding character. | Carousel
2026-09-21 | Mon | 1 | Interest Generation | FZS Hybrid | Explain Smart Motor Generator and Stop & Start System benefits through a simple everyday traffic scenario. | Motion
2026-09-23 | Wed | 1 | Purchase Generation | FZS V2 DD | Model-specific offer reminder combining price communication with practical value and a showroom visit CTA. | Static
2026-09-24 | Thu | 1 | Interest Generation | FZS V4 | Technology explainer covering Y-Connect, digital meter information and rider-relevant connected convenience. | Motion
2026-09-25 | Fri | 1 | Lifestyle Aspiration | R15 Series | Track-inspired aspiration content built around precision design, aerodynamic presence and disciplined performance culture. | Reel
2026-09-27 | Sun | 1 | Lifestyle Aspiration | FZ-X | World Tourism Day journey story celebrating responsible discovery of Bangladesh through a relaxed, culturally curious touring perspective. | Reel
2026-09-28 | Mon | 1 | Purchase Generation | FZ25 | Offer-led conversion content connecting the FZ25's performance and Dual Channel ABS with a direct showroom enquiry CTA. | Static
2026-09-29 | Tue | 1 | Lifestyle Aspiration | MT-15 V2 | Street-culture visual story focused on agile character, bold presence and the energy of a purposeful night-to-day city lifestyle. | Motion
2026-09-30 | Wed | 1 | Customer Experience | FZS Hybrid | Month-closing customer story demonstrating practical hybrid ownership across a realistic weekday routine. | Reel
Planning Dependencies |  |  | Core Objective – September 2026
Offer Static | Tuesday, 1 Sep 2026 |  | 1 | Lead the month with a clear static offer announcement and follow with a video explanation on 3 September.
Offer Video | Thursday, 3 Sep 2026 |  | 2 | Use World Clean Air Day to build responsible mobility relevance without unsupported environmental claims - Model Hybrid
Clean Air Day | Monday, 7 Sep 2026 |  | 3 | Generate stronger consideration for FZS V2 DD, FZS V4 and FZS Hybrid through feature education and customer proof.
Tourism Day | Sunday, 27 Sep 2026 |  | 4 | Use World Tourism Day to connect Yamaha with responsible discovery, local journeys and lifestyle aspiration.
Total Posts | 20 |  | 5 | Maintain one dedicated R15 and one MT-15 content while concentrating conversion weight on priority FZS models.

## September Logic
September 2026 — Content Logic & Data Backup
Product | Jul'26 Units | Jul'26 Share | 12-Mo Share Shift | Aug'26 Retail | Sep'26 Forecast | Posts This Month | Pillar Split | Why This Allocation
FZS V2 (DD) | 3,950 | 50.8% | +4.8 pts YoY | 2739 | ~4,210 | 4 | 1 Purchase / 3 Experience | Volume engine, still gaining share. No awareness/interest needed — content is pure conversion + proof.
FZS V4 | 1,968 | 25.3% | -4.2 pts YoY | 1311 | ~2,210 | 3 | 1 Purchase / 2 Experience | Still top-two by volume but losing share to V2 and Hybrid. Keeps a light interest thread to defend its TCS/ABS differentiation.
FZS Hybrid | 761 | 9.8% | +9.8 pts YoY (new) | 683 | ~800-950 | 5 | 2 Interest/Awareness / 1 Purchase / 2 Experience | Fastest-growing model in the lineup; +17% MoM Jun->Jul momentum. Heaviest Interest weight this month to clear the technology-comprehension barrier (no external charging) before the September purchase peak.
FZ25 | 73 | 0.9% | -0.7 pts YoY (units -34%) | 58 | ~100 | 3 | 1 Awareness / 1 Interest / 1 Purchase | Steepest decline in the lineup outside Fazer. Given the brief's aggressive/speed positioning, the funnel gap is above Interest, so Awareness leads this month's arc.
Fazer | 229 | 2.9% | -4.5 pts YoY (units -54%) |  | ~235 | 1 | 1 Experience | Steepest YoY decline of any model. Deliberately no Purchase post this month — rebuilding consideration comes first.
FZ-X | 272 | 3.5% | -0.9 pts YoY |  | ~300 | 3 | 1 Awareness-Interest / 1 Purchase / 1 Experience | Softer decline than Fazer, so it can carry one purchase post alongside a lifestyle/identity post.
MT15 | 81 | 1.0% | +0.1 pts YoY (units +37%) |  | ~80 | 2 | 1 Interest / 1 Purchase | Genuine YoY grower on a lifestyle-led approach — one UGC-style post keeps the format going without over-investing budget.
R15 Series | 130 | 1.7% | -0.2 pts YoY (flat) |  | ~170 | 2 | 1 Interest / 1 Experience | Flat despite continued lifestyle investment — this month tests a heavier purchase push against the usual lifestyle content (see Nov 28 for the lifestyle counterpart to compare).
Methodology & data notes
• September is forecast as the seasonal purchase peak for nearly every model (see Section 4 of the market trend report) — every core model historically dips in August and peaks in September. Content this month is deliberately purchase-heavy relative to August's funnel-building posture.
• Total market forecast for September 2026: ~8,400 units, essentially flat vs. September 2025's actual 8,355 — this is a share-capture month, not a category-growth month. Every unit gained comes from a competitor.
• The brief's instruction to 'push slower products' in September is reflected in FZ25 and Fazer each getting an Awareness-led arc rather than jumping straight to offers, since their declines are steep enough that a purchase post alone would have little to convert against.
Source: Product-wise retail sell-out data, Yamaha Bangladesh Retail Sales Reports (Aug'25, Sep'25, Oct'25, May'26, Jun'26, Jul'26), aggregated in the Market Trend Analysis & Q3 FY26 Content Strategy report.

## Staff ID & Designation
Name | Staff ID | Designation | Email Address
11465 | Hossain Mohammad Option | BM,Yamaha | option@aci-bd.com
18415 | Mirajul Alam | DGM | mirajul@aci-bd.com
14814 | Md. Zahidul Islam | AGM | zahidul@aci-bd.com
23689 | Rizwan UZ Zaman | Manager | rizwan@aci-bd.com
29842 | Nabanita Islam | APM,Yamaha | Nabanita@aci-bd.com
24082 | Richard Chakma | APM,Yamaha | richard@aci-bd.com
24784 | Sudipta Adhikary | APM,Yamaha | adhikary@aci-bdcom
32320 | Kamrul Islam Anik | AM | Kamrul.Anik@aci-bd.com
27614 | Amit Sarker | Sr.Executive | amitsarker@aci-bd.com
42993 | Efaz Ahmed | Sr.Executive | efaz@aci-bd.com
17618 | Marzia Tabassum Fariha | Sr.Executive | Tabassum@aci-bd.com
32182 | Nazia Bintay Ashraf | Sr. Ex-DM | Nazia.Ashraf@aci-bd.com
38629 | Sourav Bikash Mojumder | Sr.PE | Sourav.Bikash@aci-bd.com
34790 | Kazi Rifat Mahmud | Sr.BE | rifat.mahmud@aci-bd.com
32310 | Md. Robin | GD | robin@aci-bd.com
37586 | AlMamun | GD | mamun.gd@aci-bd.com
38352 | Mir Sabbir Ahammed Chowdhury | PE | Sabbir.ahammed@aci-bd.com
39048 | Mahabubur Rahman | Aactivity Executive | motor.mahbub@aci-bd.com
40664 | Nasrin Sultana Nishi | PE | Sultana.Nishi@aci-bd.com
42994 | Swagata Kumar Saha | PE | Swagata@aci-bd.com
40663 | Samiun Nabi | Executive | samiun@aci-bd.com
41150 | Istiak Md. Anam Arnob | Executive-Dm | arnob@aci-bd.com
44040 | SM Abu Nasim Shakil | Executive | Nasim.Shakil@aci-bd.com
37587 | Ruckmana Zaman | Executiver- QM | Ruckmana@aci-bd.com
41351 | Md. Nabil Uddin Sarker | Executive-DM | Nabil.Sarker@aci-bd.com
46090 | MD Abu Bakkar Siddik | PE | Abu.siddik@aci-bd.com
44610 | Mithila Priasa | PE | priasa@aci-bd.com
44249 | Azmyen Mustafa Chowdhury | PE | azmyen@aci-bd.com
43325 | Mirza Arafin | GM | Arafin@aci-bd.com
46219 | Ashif Ahmed (Niloy) | Deputy Manager, | Ashif.Ahmed@aci-bd.com